## Strategy Analysis
STRATEGY ANALYSIS
Business Need | To automate all the library activities with a software to find all the books with one click, issue and reissue books, manage all the data efficiently with a Library Management System.
Problem | The current manual library system, requires more time to manage, issue and find books. It also difficult to maintain student data and keep records of the books with the students
Root cause | 1.Problems with manual library: 2.A lot of time is wasted managing the manual library. 3.The number of employees needed to manage the library is high. 4.Fine calculation is a tedious and time-consuming affair. 5.No reports could be generated on books issued due to the manual system. 6.It is difficult to manage 4 million books present in the library. 7.Students could deposit the books only in the library timings

## Personas
PERSONAS
Student
Name: | Jasir Shah
Role: | He is a student who needs to check book data for borrowing and returning books
Goals( Expectation from the system) | Check book availability and borrowed book status online
Typical system usage: | Once a week
Preferances | Online check
Other information | N/A
Library Admin
Name: | Jonathan Myres
Role: | He's a library admin who checks book data for students and keeps track of books
Goals( Expectation from the system) | Check book availability and student data on book transactions with a software
Typical system usage | Everyday
Preferances | Check in the software in the library
Other information | N/A
Library Manager
Name: | John Wick
Role: | He's a library manager who makes sure of book availability and proper software functioning
Goals( Expectation from the system) | Check book availability and easy extraction of student data and book data with the software
Typical system usage | Twice a month
Preferances | Check through online
Other information | N/A

## Value Tree
VALUE TREE
Problem or opportunity | Benefits = Potential Value to be realized by the organization | Indicators/Outcomes | Epics ( High level features of the product)
Launch a new library management system | Reduced overheads and increased productivity | Less staffs needed | Easy book location access through the LMS
|  | More book management work done | RFID tag on all materials for easy data visuaization by scanning through the LMS
| Cost Reduction | Reduced staff costs | Easy data extraction by search through LMS
|  | Reduced loss of money by poor fees and fine calculation method | Automatic fine calculation by the LMS
| Dynamic report generation | Instant report on book availability and status | Book stock details all uploaded in the LMS
|  | Instant report on fine and fees collection | Total revenue reports on fees and fine are provided by the LMS

## Epics
EPICS
Epic No | Epics ( High level features of the product) | Acceptance criteria: Conditions need to be met for the epic | Epic Estimation: Sum of estimation of individual stories to arrive at definitive estimate
E01 | Book location access functionality: As a user I need a login to access the system and search for book availability and access other features | *Should have different login modes for different type of user * Should have a search tool in the software to access the books and its details | 20SP
E02 | RFID tag functionality: As an admin user I need to scan the RFID tag of any material and know its details through library reader | *Should be able to scan the book with RFID reader for material info *Student book transaction info should be able to upload in the RFID tag | 40SP
E03 | Student data functionality: As an admin user I need to access the student data based on book transactions with the library | * Student data should be accessed with a student ID to refer book transactions, deposit date and fine pendings | 30SP
E04 | Fine calculation functionality: As a user I need to view fees and fine details in the LMS | * The fine should be automatically calculated and displayed in the student data when the return date is exceeded | 20SP
E05 | Books report fuctionality: As a library management user I need to view the book stock details and new arrivals | * Book stock details should be kept up to date * New arrivals should be updated in the system | 40SP
E06 | Revenue report functionality: As a library management user I need to get the revenue report on fees and fine received | * Revenue through fees and fine pendings should be updated in the system by the admin for instant reports | 30SP

## Stories
STORIES
Reference Epic No | Story No | Story description | Acceptance criteria | Story Estimation
E01 | S01 | As a student user, I need to login with my student ID and access data like book availability, book transactions and pending fines | * Should be able to choose the type of user to proceed *Just neccessary features for a student is visible | 5SP
| S02 | As an admin user, I need to login with my admin ID and access data like book availability, location, student data, book transactions, and stock details | *Should be able to access through online with ID and can access the sytem in the library to access the LMS * All features except the reports can be accessed | 10SP
| S03 | As a management user, I need to access all the reports based on the library activities like revenue reports and book stock reports. | *Should be able to have access through online and can download reports online for further use | 5SP
E02 | S04 | As a LMS student user, I need to scan the book in the library reader for details and deposit the books in the RFID book collector | *All RFID data should be connected to the sytem before hand *And every individual RFID data can be attached with a student data when issued | 20SP
| S05 | As a LMS admin user, I need to scan the book in the reader and upload the student info to the RFID data | * The admin should only have the access to upload the student data in the RFID data through his system and scanner | 20SP
E03 | S06 | As a LMS user, I need to access the student data with their student ID to know their book transaction details like issue/ return dates | * The student ID can be scanned or student ID can be searched by number in the LMS for student data * Instant transaction details should be viewed to inform to the student | 15SP
| S07 | As a LMS user, I need to access student data on pending fines | * The bill for the pending fines should be downloaded by the admin to give the student | 15SP
E04 | S08 | Automatic fine calculation by the LMS when book return date exceeds | *Automatic date calculator for return/issue * Automatic fine calculator activation after the date exceeds | 10SP
| S09 | Reminder message on book returns and fines sent to the book user | * Reminder message sent as SMS and mail | 10SP
E05 | S10 | Automatic report updates to the system on book stock and book info when scanned by the admin on stacking | * Auto data saver with a portable RFID scanner to save in the LMS | 25SP
| S11 | Automatic report updates to the system on new material arrivals when scanned by the admin on stacking | * Auto data saver with the RFID scanner before stacking any new material | 15SP
E06 | S12 | Revenue report on total fine received is updated in the system by the admin for instant reports | * Downloadable and printable feature of the report by thte manageent | 20SP
| S13 | Pending fines are updated automatically in the system for instant reports | * Downloadable and printable financial statement feature | 10SP

## Release Planning
Release Planning
Spirint duration | 2 weeks
Spirint 0 | - | Infra setup, Product backlog refinement
Spirint 1 | 15SP | S01,S02
Spirint 2 | 25SP | S03,S04
Spirint 3 | 15SP | S05
Spirint 4 | 5SP | Buffer spirint: Testing and left over work
Release 1 ( E01,E02 ) | 60SP | Release user access to book data and book transaction
Spirint 5 | 30SP | S06,S07
Spirint 6 | 15SP | S08,S09
Spirint 7 | 5SP | Buffer spirint: Testing and left over work
Release 2 ( E03,E04) | 50SP | Release user access to fine calculation and student data
Spirint 8 | 40SP | S10,S11
Spirint 9 | 25SP | S12,S13
Spirint 10 | 5SP | Buffer spirint: Testing and left over work
Release 3 (E05,E06) | 70SP | Release user access to all features including report access and extraction